## About PC
About the PC
Name | Varun Gandhi
Email | varun@1thing.design
Mobile | 9650397667
About the Product
Name | 1THING
Labels | design, design-as-a-service, ux, ui, workforce-as-a-service, agency
Link | https://1thing.io
Kick off date | 12.12.2017
Renewal date | 12.01.2018

## Right Design Team
Name | Role | Email | Phone | Available | Not Available | Anything else
Shashank Hudkar | Design Lead | shashank@1thing.design | 9910602019 | Anytime
S UX
S UI
UX Writer
Other Skill
Other Skill
Steve Jobs | Partner Happiness | steve@1thing.design | 8375008375
Divanshu Thakral | COO | divanshu@1thing.design | 9958198311
Varun Gandhi | CEO | varun@1thing.design | 9650397667
Design Journeys | CC | journeys@1thing.design

## Resources
Name | Purpose | Link
Workspace | Communications | Link
Google Drive | Documents | Link
Marvel Link | Prototypes | Link
Zeplin | Assets | Link
HTML | Frontend | Link
Other Tool | Purpose | Link
Other Tool | Purpose | Link
Other Tool | Purpose | Link

## Things To Do
Things To Do | Stages | Ownership | Hours (Min) | Hours (Max) | Dates
Things to plan | Planning | DL | 50 | 70
Things to direct |  | DL
Things to review |  | DL
Things to manage |  | DL
Things to deliver |  | DL
Understand: 1THING | Sprint | DL | 20 | 30
Doc: Product & Users |  | DL
Concept Design | Sketch | S UX | 20 | 30
Information Architecture | UX | S UX | 60 | 90
Wireframe Direction |  | S UX
Wireframes |  | Mid
UX Prototype |  | Mid
Moodboard | UI | S UI
Visual Direction |  | S UI
Visual Designs |  | Mid
UI Prototype |  | Mid | 60 | 90
Assets & Guides | Handoff | Mid | 10 | 20
Working with developers | Support | Mid | 20 | 30
|  |  | 360 | 360

## Daily Updates
Dates | Things To Do | Stages | Add a State | Add a Tag | Link | Overall Status | Comments, if any | Hours: DL | Hours: S UX | Hours: S UI | Hours: Mid | Hours Spent
2018-01-12 | Understand: 1THING | Sprint | Completed | We have shared & waiting for the feedback | MoMs: 12.1.2018 | On time | We have had a good first call & the excitement has quadrupled. | 2 | 0 | 0 | 0 | 2
2018-01-13 | Things to direct | Planning | In Progress | We are working on it | MoMs: 13.1.2018 | Some delay |  | 2 | 1 | 0 | 0 | 3
2018-01-14 | Doc: Product & Users | Sprint | In Progress | We have shared & waiting for the feedback | Doc: 14.1.2018 | Problem |  | 8 | 2 | 1 | 0 | 11
2018-01-15 | [11 empty] | 0
2018-01-16 | [11 empty] | 0
2018-01-17 | [11 empty] | 0
2018-01-18 | [11 empty] | 0
2018-01-19 | [11 empty] | 0
2018-01-20 | [11 empty] | 0
2018-01-21 | [11 empty] | 0
2018-01-22 | [11 empty] | 0
2018-01-23 | [11 empty] | 0
2018-01-24 | [11 empty] | 0
2018-01-25 | [11 empty] | 0
2018-01-26 | [11 empty] | 0
2018-01-27 | [11 empty] | 0
2018-01-28 | [11 empty] | 0
2018-01-29 | [11 empty] | 0
2018-01-30 | [11 empty] | 0
2018-01-31 | [11 empty] | 0
2018-02-01 | [11 empty] | 0
2018-02-02 | [11 empty] | 0
2018-02-03 | [11 empty] | 0
2018-02-04 | [11 empty] | 0
2018-02-05 | [11 empty] | 0
2018-02-06 | [11 empty] | 0
2018-02-07 | [11 empty] | 0
2018-02-08 | [11 empty] | 0
2018-02-09 | [11 empty] | 0
2018-02-10 | [11 empty] | 0